## Agile Product Backlog
AGILE PRODUCT BACKLOG TEMPLATE
TASK ID | TASK NAME | SPRINT # | ASSIGNED TO | START | FINISH | STORY | SPRINT READY | PRIORITY | STATUS | STORY POINTS | ASSIGNED TO SPRINT
|  | Sprint 1 | Team 3 | 2021-02-23 | 2021-03-05
| Create a healer and create a nation with 3 tribes and 3 people types | " " | Robert Rabinovich | 2021-02-23 | 2021-02-23 | Yes | Yes | Medium | Complete | 2 | Yes | This section is for the drop-down list
| Created a nation with 3 tribes and 3 people | " " | Cory Little | 2021-02-23 | 2021-02-23 | Yes | Yes | Medium | Complete | 1 | Yes | Yes | High | Complete
| Created a nation with 3 tribes and 3 people | " " | Ben Jones | 2021-02-23 | 2021-02-23 | Yes | Yes | Medium | Complete | 1 | Yes | No | Medium | In Progress
| Start UML Diagram | " " | Cory Little | 2021-02-25 | 2021-02-25 | Yes | Yes | Medium | Complete | 2 | Yes
| Start UML Diagram | " " | Robert Rabinovich | 2021-02-25 | 2021-02-25 | Yes | Yes | Medium | Complete | 2 | Yes
| Start UML Diagram | " " | Ben Jones | 2021-02-25 | 2021-02-25 | Yes | Yes | Medium | Complete | 2 | Yes
| Finished UML Diagram | " " | Ben Jones | 2021-03-02 | 2021-03-02 | Yes | Yes | Medium | Complete | 2 | Yes
| Finish Java Documentation | " " | Robert Rabinovich | 2021-03-02 | 2021-03-02 | Yes | Yes | Medium | Complete | 1 | Yes
| FIguring out the code | " " | Cory Little | 2021-03-02 | 2021-03-02 | Yes | Yes | Medium | Complete | 8 | Yes
|  | Sprint 2 | [10 empty] | Low | Not Started
[6 empty] | Yes | Yes | High | In Progress |  | Yes
Sprint 3
In Progress
Sprint 4
Sprint 5
Sprint 6
Sprint 7