## Agile Sprint Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 6 | DAY 5 | SPRINT REVIEW
User Story #1 Create a healer and create a nation with 3 tribes and 3 people type | 2
Task Created a nation with 3 tribes and 3 people | 0.5 | Robert Rabinovich | Complete | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
Task Created a nation with 3 tribes and 3 people | 0.5 | Cory Little | Complete | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
Task Created a nation with 3 tribes and 3 people | 0.5 | Ben Jones | Complete | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
User Story #2 UML Diagram | 3
Task Complete UML Diagram | 2.5 | Ben Jones | Complete | 2 | 1 | 1 | 0 | 0 | 0.5 | 0 | 0
Task Check UML Diagram | 0.5 | Robert Rabinovich | Complete | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Check UML Diagram | 0.5 | Cory Little | Complete | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story #3 Java Docs | 5
Task Create the Java Docs | 1 | Robert Rabinovich | Complete | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Task Check Java Docs | 0.5 | Ben Jones | Complete | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
Task Check Java Docs | 0.5 | Cory Little | Complete | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
User Story #4 Understanding the concept of the game | 8
Task Understanding the game | 2.5 | Robert Rabinovich | Complete | 2 | 1 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
Task Understanding the game | 3 | Ben Jones | Complete | 3 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
Task Understanding the game | 2.5 | Cory Little | Complete | 2 | 1 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
TOTAL |  |  |  | 14 | 5.5 | 4.5 | 1.5 | 1.5 | 1 | 0 | 0

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Task
Task
Task
Task
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0